## TECHNICAL AND PLANNING
TECHNICAL AND DEVELOPMENT PLANNING SERVICES DEPARTMENT
2018/2019 - SERVICE DELIVERY BUDGET IMPLEMENTATION PLAN
No: | NATIONAL KPA | IDP | PERFORMANCE TARGET | UNIT OF MEASUREMENT | BUDGET | ANNUAL TARGET | QUARTER ENDING 30 SEPT |  | QUARTER ENDING 31 DEC |  | QUARTER ENDING 31 MARCH |  | QUARTER ENDING 30 JUNE
[7 empty] | TARGET | ACTUAL | TARGET | ACTUAL | TARGET | ACTUAL | TARGET | ACTUAL
1 | DEPARTMENTAL BUDGETING, FINANCIAL MANAGEMENT AND ENSURING MSCOA COMPLIANT
1.1 | FINANCIAL MANAGEMENT AND FINANCIAL VIABILITY |  | Ensure 100% spending on MIG annual expenditure programmes with no over-expenditure by 30 June 2019. | Percentage of budgeted amount spent on MIG | 17749000 | 100% MIG spent by 30 June 2019. | 30% |  | 60% |  | 80% |  | 100%
1.2 |  |  | Ensure 100% spending on INEP grant with no over-expenditure by 30 June 2019. | Percentage of budgeted INEP grant spent. | 15000000 | 100% of INE P grant to be spent by 30 June 2019 | 30% |  | 60% |  | 80% |  | 100%
1.3 |  |  | Ensure the submission of the 2018/19 adjustment budget to CFO by 15 January 2019. | Adjustment budget submitted by 15 January 2019. | 0 | Submit adjustment budget by 15 Janauary 2019, | _ | _ | _ | _ | Submit adjustment budget to CFO by 15 January 2019. |  | _ | _
1.4 |  |  | Ensure the submission of the 2019/2020 draft budget proposals to CFO by 15 March 2019 | Draft budget submitted by 15 March 2019. | 0 | Submit draft 2018/2019 to CFO by 15 March 2019, | _ | _ | _ | _ | Submit draftt budget to CFO by 15 March 2019. |  | _ | _
2 | DEPARTMENTAL MANAGEMENT
2.1 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  | Submit 4 reports to the Technical Services Portfolio Committee on the Performance of Contractors under the control of the Technical Department by 30 June 2019. | Number of reports | 0 | 4 report on Contractors submitted to technical portfolio by 30 June 2019. | 1 report |  | 1 report |  | 1 report |  | 1 report
2.2 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  | Conduct 11 departmental meetings by 30 June 2019 with all Technical Services supervisors and maintain register of meeting minutes. | Number of meetings | 0 | 11 meetings held by 30 June 2019, | 3 meetings |  | 2 meetings |  | 3 meetings |  | 3 meetings
2.3 | COMMUNITY AND SOCIAL DEVELOPMENT |  | Ensure poverty alleviation by creating new 80 EPWP contract jobs by 15 August 2018. | Number of new EPWP jobs created by 15 August 2018 | 1808000 | 80 EPWP jobs created by 15 August 2018. | Employ 80 EPWP contract workers. |  | _ | _ | _ | _ | _ | _
3 | BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENTS
3.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and 100% completion of Gobihlahla creche. | Pecentage of constrution completed | 2583000 | 100% Construction of the creche by 30 June 2019. | Advertise tender and appoint service provider. |  | Site establishment and construction of foundation. (30%) |  | Constrction of walls, ablution block and roofing (60%) |  | Wall plaster, windows and fencing of the creche (100%)
3.2 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and 100% completion of Mpevu creche by 30 June 2019. | Pecentage of constrution completed | 2583000 | 100% completion of construction of creche. | Advertise tender and appoint service provider. |  | Site establishment and construction of foundation. (30%) |  | Constrction of walls, ablution block and roofing (60%) |  | Wall plaster, windows and fencing of the creche (100%)
3.3 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and 100% completion of Ntombokazi creche by 30 June 2019, | percentage of construction completed. | 2583000 | 100% completion of construction of creche. | Advertise tender and appoint service provider. |  | Site establishment and construction of foundation. (30%) |  | Constrction of walls, ablution block and roofing (60%) |  | Wall plaster, windows and fencing of the creche (100%)
3.4 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the rehabilitation of a total of 6km urban roads in wards 2 and 3 by 30 June 2019, | Number of kilometers completed | 6000000 | 6km of urban roads to be constructed by 30 June 2019. | Advertise tender and appoint service provider. |  | Site establishment and construction of foundation. (30%) |  | Constrction of walls, ablution block and roofing (60%) |  | Wall plaster, windows and fencing of the creche (100%)
3.5 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the regravelling of the 5km of rural raods: Nungwini (Ward 1), Mfule (Ward 4)& Manzawayo (Ward 5) by 30 June 2019 | Number of kilometers completed | 4000000 | 5km of rural roads to be regravelled by 31 March 2019. | Advertise tender and appoint service provider. |  | 2km of rural roads to be regravelled in the second quarter. |  | 3km of rural roads to be regralled in the third quarter ( A total of 5km of rural road in Nungwini, Mfule & Manzawayo to be regravelled by 31 March 2019. |  | _ | _
4 | OPERATION AND MAINTENANCE (BUILDINGS AND ROADS)
4.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | A7.1.1 | Ensure the 100% completion of maintenance projects of Council buidlings by 30 June 2019. | Rand value of budgeted amount spent on maintenance | 1500000 | 100% completion of maintenance of council buidlings by 30 June 2019. | 30% completion |  | 50% completion |  | 70% completion |  | 100% completion
4.2 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | A.7.2.1 | Ensure the 100% spending and 100% completion of road infrastructure maintenance by 30 June 2019. | Rand value of budgeted amount spent on maintenance | 800000 | 100% completion of maintenance of road infrastructure by 30 June 2019. | Advertise and appoint service provider. |  | 50% completion of maintenance of roads |  | 70% completion of maintenance of roads |  | 100% completion of all maintenance of roads projects
5 | WASTE MANAGEMENT
5.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the appointment of a service provider to transfer of waste from the municipal transfer station to a registrerd land fill site by 31 December 2018 | Date service prover appointed | 460000 | Appoint service provider by 31 December 2018, | Advertise tender and appoint service provider by 31 December 2018, |  | Transfer of waste from the municipal transfer station to a registrerd land fill site |  | Transfer of waste from the municipal transfer station to a registrerd land fill site |  | Transfer of waste from the municipal transfer station to a registrerd land fill site
5.2 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the purchasing of 50000 refuse bags by 30 June 2019. | Number of refused bags purchased. | 190000 | Ensure the purchasing of 50000 refuse bags by 30 June 2019. | Purchase 12500 refuse bags by 30 September 2018 |  | Purchase 12500 refuse bags by 31 December 2018 |  | Purchase 12500 refuse bags by 31 March 2019 |  | Purchase 12500 refuse bags by 30 June 2019
5.3 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the purchasing of protective clothing by 31 December 2018 | Date of purchase | 150000 | Purchase protectve clothing | Advertise and appoint service provider |  | Purchase protective clothing. |  | _ | _ | _ | _
5.4 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensuring the purchasing of 6 refuse skips and 20 waste bins by 30 December 2018 | Number of skips and waste bins purchased | 500000 | Purchasing of 6 refuse skips and 20 waste bins by 30 December 2018 | Advertise and appoint service provider. |  | Ensure the supply and delivery of 6 refuse skips and waste bins by 31 December 2018 |  | _ | _ | _ | _
6 | ELECTRICAL PROJECTS AND ELECTRICAL MAINTENANCE
6.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 246 new connections to households in Soqiwa Makhasaneni area, for the first time by 30 June 2019. | Number of new electricity connections completed | 12000000 | 246 Connections completed by 30 June 2019. | Pre-market and designs |  | 100 Connections |  | 100 Connections |  | 46 Connections | _
6.1
6.2 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 500 new connections to households in Thubalethu Township, for the first time by 30 June 2019. | Number of new electricity connections completed | R3,000,000.00 | 500 connections completed by 30 June 2019. | Pre-market and designs |  | 100 Connections |  | 100 Connections |  | 300 Connections
7 | BACK TO BASICS
7.1 | INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION |  | Ensure the submission of 4 quarterly report to MANCO by 30 June 2019. | Number of B2B reports submitted to MANCO | 0 | 4 Reports submitted to MANCO by 30 June 2019, | 1 B2B report submitted to MANCO. |  | 1 B2B report submitted to MANCO. |  | 1 B2B report submitted to MANCO. |  | 1 B2B report submitted to MANCO.
8 | TOWN AND REGIONAL PLANNING
8.1 | COMMUNITY AND SOCIAL SERVICES |  | Ensure the reviewal and approval of the Spatial Development Framework by Council by 30 June 2019. | Approved SDF by 30 June 2019. | 150000 | Approved SDF by 30 June 2019. | Advertise and appoint service provider. |  | Status quo report to be completed by 31 December 2018 |  | Advertise draft SDF by 31 March 2019. |  | Approval of Final SDF by Council by 30 June 2019.
8.2 | COMMUNITY AND SOCIAL SERVICES |  | Ensure the registration of 40 sites by 31 December 2018. | Number and date of Registration of sites with Surveyor General. | 174000 | Registration of 40 residentail sites by 31 December 2018. | Approval of 40 sites |  | Approval of 40 Sites by Surveyer general by 31 December 2018. |  | _ | _ | _ | _
9 | POLICY DEVELOPMENT
9.1 | INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION |  | Ensure the development and approval of the consolidated operations and Maintenance Plan by 31 December 2018 | Date of approval of Operation and Maintanance Plan | R | Approved policy by 31 December 2018 | Advetise and appoint service provider in the first quarter. |  | Approval of O&M Plan by Council by 31 December 2018. |  | _ | _ | _ | _
Note on B16: idp:

## Shadow 02.04.09 (hidden)
Dep-code | Item-code | Vote-code | original | 31/03/2009 | Expenses/income[13] | Expenses/income[10] | Expenses/income[12] | Expenses/income[1] | Expenses/income[2] | Expenses/income[3] | Shadow-costing
201 | 532 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 532 | 2 | 90000 | 72624.46 | 72624.46 | 69624.46 | 3000 | 0 | 0 | 0 | 0
201 | 544 | 2 | 237200 | 148241 | 148241 | 67309 | 0 | 0 | 19440 | 0 | 26845.3
202 | 632 | 2 | 4000000 | 2820887.97 | 2820887.97 | 29042.84 | 0 | 468490 | 89379.77 | 183135.62 | 0
202 | 632 | 3 | 2000000 | 1911060.91 | 1911060.91 | 1053251.14 | 334001.66 | 0 | 226696.45 | 0 | 0
204 | 532 | 10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 13 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 14 | 16100 | 16100 | 16100 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 15 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 16 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 17 | 17200 | 17200 | 17200 | 17200 | 0 | 0 | 0 | 0 | 0
204 | 532 | 18 | 40000 | 9100 | 9100 | 0 | 0 | 9100 | 0 | 0 | 0
204 | 536 | 7 | 11300 | 11298 | 11298 | 0 | 0 | 0 | 0 | 0 | 0
204 | 544 | 3 | 23400 | 23391.02 | 23391.02 | 8920 | 0 | 0 | 0 | 0 | 0
204 | 544 | 4 | 19100 | 19040 | 19040 | 0 | 0 | 0 | 695 | 0 | 0
205 | 532 | 5 | 500000 | 418528.52 | 418528.52 | 0 | 418528.52 | 0 | 0 | 0 | 0
205 | 532 | 6 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 536 | 21 | 142800 | 142750.1 | 142750.1 | 0 | 0 | 0 | 0 | 0 | 0
205 | 536 | 22 | 70000 | 59111 | 59111 | 1836 | 0 | 0 | 0 | 11443 | 4990
206 | 532 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 536 | 1 | 7000 | 2028.93 | 2028.93 | 2028.93 | 0 | 0 | 0 | 0 | 0
208 | 544 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 536 | 0 | 30500 | 30447.5 | 30447.5 | 1690 | 0 | 0 | 0 | 0 | 0
209 | 544 | 0 | 10000 | 2200 | 2200 | 0 | 2200 | 0 | 0 | 0 | 6300
210 | 532 | 0 | 6850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 536 | 2 | 23000 | 19842.1 | 19842.1 | 0 | 0 | 17824.56 | 2017.54 | 0 | 0
211 | 536 | 3 | 10000 | 9686.81 | 9686.81 | 0 | 0 | 8684.21 | 1002.6 | 0 | 0
211 | 536 | 4 | 14400 | 12950 | 12950 | 0 | 0 | 0 | 0 | 12950 | 0
211 | 544 | 0 | 12000 | 5447.5 | 5447.5 | 5447.5 | 0 | 0 | 0 | 0 | 0
212 | 532 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 532 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 536 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 544 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8627.5
213 | 536 | 1 | 4400 | 4310 | 4310 | 0 | 0 | 0 | 0 | 0 | 0
213 | 544 | 0 | 35000 | 31430 | 31430 | 16930 | 0 | 0 | 0 | 14500 | 1290
216 | 528 | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 528 | 1 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 11 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 12 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 13 | 70000 | 34500 | 34500 | 34500 | 0 | 0 | 0 | 0 | 0
216 | 532 | 14 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 15 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 16 | 8000 | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0
216 | 532 | 17 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0
216 | 532 | 18 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38780
216 | 532 | 19 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14900
216 | 532 | 20 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94660
216 | 532 | 21 | 1231000 | 137256.04 | 137256.04 | 15200 | 0 | 0 | 0 | 122056.04 | 0
216 | 532 | 22 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 23 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 536 | 0 | 84000 | 74485.37 | 74485.37 | 0 | 0 | 0 | 0 | 0 | 0
219 | 528 | 2 | 64500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 32 | 400000 | 171671.16 | 171671.16 | 50946.16 | 53351 | 0 | 57974 | 0 | 114512
219 | 532 | 34 | 55000 | 54694.7 | 54694.7 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 35 | 630000 | 439161.53 | 439161.53 | 377764.65 | 0 | 58000 | -7122.81 | 10519.69 | 105327.2
219 | 532 | 38 | 55500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 46 | 470000 | 347676.17 | 347676.17 | 0 | 0 | 0 | 285791.86 | 0 | 66785
219 | 532 | 47 | 24000 | 9305.5 | 9305.5 | 4865.5 | 0 | 0 | 0 | 0 | 0
219 | 532 | 48 | 200000 | 198280 | 198280 | 0 | 0 | 0 | 198280 | 0 | 0
219 | 532 | 49 | 17000 | 6379 | 6379 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 50 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55957.7
219 | 532 | 51 | 2000000 | 184333.79 | 179053.09 | 0 | 0 | 0 | 0 | 184333.79 | 0
219 | 532 | 52 | 35000 | 24490 | 24490 | 0 | 4500 | 0 | 0 | 19990 | 0
219 | 532 | 53 | 150000 | 103100 | 103100 | 0 | 103100 | 0 | 0 | 0 | 0
219 | 532 | 54 | 65000 | 60264.35 | 60264.35 | 0 | 33314.35 | 0 | 26950 | 0 | 0
219 | 532 | 55 | 3000000 | 2086376.41 | 2089877.41 | 281129.05 | 0 | 546491.51 | 0 | 1250219.46 | 30000
219 | 532 | 56 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 57 | 300000 | 116600 | 116600 | 0 | 0 | 0 | 116600 | 0 | 116600
219 | 532 | 58 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 59 | 47500 | 47500 | 47500 | 0 | 47500 | 0 | 0 | 0 | 0
219 | 532 | 60 | 30000 | 17750 | 17750 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 61 | 1000000 | 62830 | 102830 | 0 | 31415 | 0 | 0 | 0 | 100800
219 | 532 | 62 | 7000 | 1680.96 | 1680.96 | 0 | 0 | 0 | 0 | 1680.96 | 0
219 | 532 | 63 | 800000 | 70012.53 | 70012.53 | 0 | 70012.53 | 0 | 0 | 0 | 0
219 | 532 | 64 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 65 | 72500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
219 | 532 | 66 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 544 | 0 | 34000 | 30658.6 | 30658.6 | 0 | 30658.6 | 0 | 0 | 0 | 0
219 | 628 | 0 | 1430000 | 1430000 | 1430000 | 0 | 910254.89 | 272005.01 | 0 | 0 | 0
219 | 632 | 17 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 20 | 220000 | 162710.6 | 162710.6 | 14719.6 | 0 | 0 | 0 | 147991 | 35434.5
219 | 632 | 23 | 6610000 | 5070 | 5070 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 24 | 488300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 25 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 26 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 27 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 532 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 544 | 0 | 1300 | 1208.25 | 1208.25 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 48 | 800000 | 565937.96 | 565937.96 | 0 | 80511.97 | 0 | 248120 | 237305.99 | 224969.85
222 | 572 | 49 | 400000 | 59784.74 | 59784.74 | 0 | 0 | 0 | 0 | 59784.74 | 0
222 | 572 | 50 | 400000 | 0 | 0 | 0 | 0 | -349168.2 | 0 | 0 | 0
222 | 572 | 51 | 829500 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 12320.4
222 | 572 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 56 | 850000 | 315508 | 315508 | 48201.76 | 92370.73 | 0 | 69802.15 | 74056.06 | 0
222 | 572 | 57 | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 58 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 59 | 13035000 | 1767050.54 | 1767050.54 | 0 | 1409507.92 | 357542.62 | 0 | 0 | 0
222 | 572 | 60 | 2000000 | 242887.5 | 242887.5 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 61 | 6110900 | 181065.13 | 181065.13 | 0 | 0 | 0 | 0 | 25829.5 | 0
222 | 572 | 62 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 63 | 5000000 | 635761.8 | 635761.8 | 0 | 0 | 0 | 0 | 635761.8 | 0
222 | 572 | 64 | 3580700 | 380602.99 | 638314.99 | 0 | 0 | 0 | 55076.72 | 300696 | 0
222 | 572 | 65 | 480000 | 75398.81 | 82733.21 | 11747.48 | 23875.33 | 0 | 26664.3 | 0 | 25242.5
222 | 572 | 66 | 4107000 | 222703.64 | 222703.64 | 0 | 32982.2 | 0 | 80735.11 | 30434.03 | 0
222 | 572 | 67 | 300000 | 7674.33 | 7674.33 | 0 | 0 | 0 | 7345.34 | 328.99 | 127.8
222 | 572 | 68 | 20800000 | 9963293.06 | 9965813.06 | 219428.47 | 518827.71 | 535 | 1433011 | 1998450.43 | 0
222 | 572 | 69 | 3605000 | 3093154.49 | 3093154.49 | 1056484.52 | 2036669.97 | 0 | 0 | 0 | 0
222 | 572 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 591 | 6 | 500000 | 109064.37 | 109064.37 | 0 | 0 | 0 | 109064.37 | 0 | 68503.29
222 | 653 | 0 | 1557700 | 1340000 | 1340000 | 592099.9 | 218218.6 | 17616.62 | 0 | 0 | 0
222 | 672 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 20 | 156600 | 143631.23 | 143631.23 | 59554.97 | 0 | 0 | 34083.46 | 0 | 0
222 | 672 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 22 | 16100 | 16024.07 | 16024.07 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 24 | 600000 | 92922.74 | 92922.74 | 0 | 0 | 0 | 0 | 92922.74 | 1025
222 | 672 | 31 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 40 | 333000 | 311443.08 | 311443.08 | 191567.93 | 0 | 0 | 0 | 0 | 0
222 | 672 | 42 | 11000 | 10339.45 | 10339.45 | 0 | 0 | 0 | 10339.45 | 0 | 0
222 | 672 | 43 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 45 | 480300 | 49706.5 | 49706.5 | 7026.5 | 0 | 27800 | 14880 | 0 | 0
222 | 672 | 47 | 467000 | 88080 | 88080 | 0 | 0 | 0 | -14880 | 0 | 0
222 | 672 | 48 | 1220400 | 509495.45 | 598604.64 | 509495.45 | 0 | 0 | -10339.45 | 0 | 0
222 | 672 | 49 | 1550000 | 89980.5 | 89980.5 | 0 | 0 | 89980.5 | 0 | 0 | 108779
222 | 672 | 51 | 3755200 | 935388.22 | 935388.22 | 14197.5 | 0 | 0 | 0 | 463850.56 | 0
222 | 672 | 55 | 2800000 | 640943.18 | 640943.18 | 0 | 0 | 0 | 0 | 168834.75 | 0
222 | 672 | 56 | 2225000 | 36905 | 36905 | 0 | 0 | 0 | 0 | 36905 | 0
222 | 691 | 1 | 1965000 | 647053.58 | 647053.58 | 0 | 0 | 0 | 0 | 647053.58 | 0
222 | 772 | 14 | 17401000 | 16946358.41 | 16950683.16 | 0 | 2574036.71 | 57458.39 | 550426.75 | 1268175.6 | 10379
222 | 772 | 16 | 1206400 | 1056431.07 | 1056431.07 | 799798.75 | 0 | 0 | 0 | 0 | 0
222 | 772 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 31 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 32 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 41 | 801800 | 123162.24 | 123162.24 | 0 | 36302.82 | 74032.45 | 12826.97 | 0 | 0
222 | 772 | 42 | 461800 | 18490.21 | 18490.21 | 0 | 18490.21 | 0 | 0 | 0 | 0
223 | 532 | 2 | 6300 | 6240 | 6240 | 6240 | 0 | 0 | 0 | 0 | 0
223 | 536 | 7 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124760
223 | 544 | 0 | 50000 | 35190 | 35190 | 35190 | 0 | 0 | 0 | 0 | 2450
224 | 528 | 1 | 125000 | 16040 | 16040 | 0 | 0 | 0 | 0 | 0 | 0
224 | 532 | 31 | 1412900 | 1216655.46 | 1216655.46 | 438738.39 | 0 | 177746.67 | 0 | 0 | 0
224 | 532 | 33 | 884000 | 374586.73 | 374586.73 | 34679.64 | 145206 | 4560 | 1980 | 183644.5 | 458000
224 | 532 | 37 | 63500 | 63459.28 | 63459.28 | 21267.68 | 0 | 0 | 0 | 0 | 0
224 | 532 | 38 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0
224 | 532 | 39 | 1240500 | 8205.36 | 8205.36 | 0 | 0 | 8205.36 | 0 | 0 | 1084840
224 | 532 | 40 | 15000000 | 5000000 | 5000000 | 0 | 0 | 0 | 5000000 | 0 | 0
224 | 532 | 42 | 104000 | 101239.04 | 101239.04 | 826.26 | 15000 | 11294 | 0 | 0 | 0
224 | 532 | 43 | 667000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 532 | 44 | 48700 | 48660 | 48660 | 0 | 0 | 0 | 48660 | 0 | 0
224 | 532 | 45 | 120000 | 118610 | 118610 | 0 | 0 | 0 | 59305 | 59305 | 0
224 | 532 | 46 | 171000 | 170465.8 | 170465.8 | 0 | 0 | 0 | 81912.5 | 88553.3 | 328.57
224 | 532 | 47 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 532 | 48 | 46000 | 45912.69 | 45912.69 | 39946.86 | 0 | 0 | 0 | 0 | 0
224 | 536 | 5 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 536 | 6 | 53000 | 4760.6 | 4760.6 | 0 | 0 | 0 | 0 | 0 | 0
224 | 536 | 7 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 572 | 2 | 353400 | 61332.3 | 61332.3 | 0 | 0 | 0 | 0 | 61332.3 | 0
224 | 632 | 7 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 632 | 8 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
224 | 632 | 9 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 632 | 10 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 632 | 11 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 544 | 0 | 11500 | 7936 | 7936 | 0 | 0 | 0 | 7936 | 0 | 0
227 | 632 | 2 | 9597500 | 7781543.65 | 7781543.65 | 1233217.02 | 0 | 2617996.37 | 415214.45 | 957064.59 | 0
227 | 636 | 0 | 17900 | 17840.34 | 17840.34 | 0 | 0 | 0 | 0 | 0 | 0
228 | 632 | 1 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45350.23
228 | 832 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 89686.08 | -89686.08 | 0
229 | 532 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 532 | 0 | 40000 | 37990 | 37990 | 0 | 0 | 0 | 0 | 37990 | 0
230 | 536 | 3 | 21700 | 21665 | 21665 | 0 | 0 | 0 | 0 | 0 | 0
230 | 544 | 0 | 22500 | 16111 | 16111 | 1551 | 14560 | 0 | 0 | 0 | 0
230 | 644 | 0 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391650.55
233 | 532 | 6 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 536 | 7 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340800
233 | 536 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 536 | 10 | 436000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341037
233 | 544 | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8376.32
233 | 632 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 632 | 3 | 22100 | 16953 | 16953 | 0 | 14880 | 0 | 0 | 0 | 0
234 | 532 | 21 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 632 | 11 | 877000 | 876213.25 | 876213.25 | 319199 | 14946 | 542068.25 | 0 | 0 | 0
234 | 632 | 14 | 5897800 | 5057266.52 | 5057266.52 | 0 | 817760.32 | 0 | 63570.76 | 3868093.11 | 0
234 | 632 | 15 | 279000 | 72930 | 72930 | 0 | 0 | 35200 | 0 | 0 | 0
234 | 632 | 16 | 399400 | 399400 | 399400 | 0 | 0 | 399400 | 0 | 0 | 0
234 | 632 | 18 | 4239500 | 3843787.49 | 3843787.49 | 76907.72 | 213465.56 | 0 | 247178.73 | 0 | 0
234 | 732 | 12 | 583000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 732 | 13 | 1200000 | 987848.5 | 987848.5 | 400417.5 | 231229.02 | 0 | 0 | 0 | 0
234 | 732 | 14 | 78000 | 77940.38 | 77940.38 | 0 | 0 | 0 | 0 | 0 | 0
234 | 832 | 1 | 12875000 | 7413207.02 | 7413207.02 | 3437527.5 | 988958 | 119982.02 | 0 | 2866739.5 | 0
234 | 832 | 2 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 532 | 10 | 3500000 | 37950 | 37950 | 0 | 0 | 37950 | 0 | 0 | 0
235 | 832 | 5 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 532 | 5 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24400
238 | 536 | 0 | 10000 | 8771.05 | 8771.05 | 0 | 0 | 0 | 0 | 0 | 0
238 | 544 | 0 | 143600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880
239 | 544 | 0 | 145500 | 146669 | 146669 | 0 | 0 | 0 | 73066 | 73603 | 0
240 | 532 | 1 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 532 | 2 | 76400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 532 | 3 | 22500 | 19248 | 19248 | 0 | 0 | 5530.24 | 0 | 0 | 0
240 | 532 | 4 | 2300 | 2250 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0
240 | 536 | 3 | 30000 | 28847.01 | 28847.01 | 0.01 | 0 | 0 | 0 | 0 | 0
240 | 544 | 2 | 36600 | 34762.6 | 34762.6 | 32905 | 0 | 0 | 0 | 0 | 0
241 | 676 | 1 | 767500 | 592622.6 | 592622.6 | 94500.15 | 22029.86 | 0 | 123661.85 | 51730.29 | 38141.4
241 | 676 | 7 | 300000 | 242114.79 | 242114.79 | 57366.57 | 68441.7 | 1016.28 | 2417.91 | 32992.33 | 4752
241 | 676 | 9 | 146400 | 146309.33 | 146309.33 | 0 | 0 | 0 | 0 | 0 | 0
241 | 676 | 10 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 676 | 11 | 400000 | 302408.9 | 302408.9 | 152235.93 | 7860.62 | 0 | 0 | 0 | 0
241 | 676 | 12 | 200000 | 159910.7 | 159910.7 | 4840 | 0 | 0 | 20704 | 38451.7 | 0
241 | 676 | 13 | 120000 | 119819.72 | 119819.72 | 4400 | 0 | 1760 | 0 | 0 | 0
241 | 676 | 14 | 250000 | 228761.82 | 228761.82 | 0 | 795.2 | 0 | 41260 | 104329.7 | 0
241 | 676 | 15 | 573000 | 62758.44 | 62758.44 | 0 | 0 | 5174.28 | 5174.28 | 46948.14 | 179018
241 | 676 | 16 | 500000 | 19975.8 | 19975.8 | 0 | 13785.8 | 6190 | 0 | 0 | 0
242 | 532 | 23 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 24 | 810000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 25 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 26 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 27 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 28 | 19900 | 19900 | 19900 | 0 | 0 | 0 | 0 | 0 | 0
242 | 536 | 3 | 40000 | 35908.9 | 35908.9 | 7500 | 0 | 0 | 0 | 0 | 0
242 | 536 | 7 | 30000 | 28210.33 | 28210.33 | 0 | 0 | 28210.33 | 0 | 0 | 0
242 | 536 | 8 | 33000 | 32280.53 | 32280.53 | 0 | 0 | 0 | 0 | 0 | 0
242 | 544 | 0 | 41300 | 20095.47 | 20095.47 | 0 | 0 | 0 | 0 | 0 | 0
242 | 632 | 3 | 1910000 | 1502077.14 | 1502077.14 | 17147.4 | 0 | 0 | 0 | 0 | 0
242 | 632 | 5 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 632 | 6 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 632 | 7 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 536 | 2 | 525500 | 237992.68 | 237992.68 | 41984.4 | 20992.2 | 0 | 78542.31 | 57550.11 | 0
243 | 536 | 3 | 800000 | 202717.62 | 202717.62 | 0 | 0 | 0 | 109350.62 | 66000 | 216912.94
243 | 536 | 7 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 544 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 632 | 0 | 7431100 | 6106603.16 | 6106603.16 | 170089.67 | 1153416.05 | 0 | 3222632.12 | 442171.16 | 387618
243 | 632 | 1 | 2706000 | 97764.77 | 156828.64 | 282400 | 40051.1 | 0 | 917156.8 | 0 | 431066
243 | 632 | 4 | 500000 | 442754.42 | 442754.42 | 99677.9 | 0 | 0 | 0 | 0 | 0
243 | 632 | 6 | 7013500 | 4257093.92 | 4257093.92 | 584300 | 160543.92 | 100800 | -877557 | 0 | 1179576.47
245 | 716 | 2 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 716 | 3 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 716 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 716 | 5 | 567000 | 13911.87 | 13911.87 | 0 | 0 | 0 | 13911.87 | 0 | 159986.53
245 | 716 | 6 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 628 | 0 | 1100000 | 479548.65 | 561144.41 | 0 | 0 | 418522.49 | 0 | 0 | 0
246 | 636 | 1 | 2000000 | 875386 | 875386 | 0 | 0 | 0 | 0 | 875386 | 0
246 | 684 | 1 | 3155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 684 | 3 | 12294700 | 6412996.91 | 6412996.91 | 0 | 2026027.39 | 76235.58 | 508078.44 | 2841721.13 | 0
246 | 884 | 1 | 28718000 | 22322287.58 | 22322287.58 | 6130483.76 | 4394117.46 | 0 | 0 | 8525954.49 | 0
246 | 908 | 1 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 9 | 50000 | 21690 | 21690 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 22 | 46779000 | 36989207.77 | 36989207.77 | 1520482.76 | 9006604.26 | 0 | 3400629.02 | 17764104.55 | 0
255 | 632 | 23 | 3500000 | 3479129.48 | 3479129.48 | 767812.71 | 156232.37 | 312325.43 | 67839.37 | 172207.64 | 0
255 | 632 | 25 | 3050000 | 3022186.7 | 3022186.7 | 0 | 348429.76 | 0 | 6730.56 | 0 | 0
255 | 632 | 27 | 4600000 | 3718321.14 | 3870420.14 | 188021.77 | 2286.63 | 874399.92 | 7343.78 | 1828464.5 | 716738.5
255 | 632 | 28 | 3100000 | 2963592.03 | 2963592.03 | 0 | 0 | 0 | 0 | 2883211.03 | 0
255 | 632 | 29 | 500000 | 47500 | 47500 | 0 | 0 | 0 | 0 | 47500 | 0
255 | 632 | 30 | 521000 | 268169.81 | 268169.81 | 0 | 0 | 4605.26 | 39125.92 | 224438.63 | 0
255 | 632 | 31 | 437400 | 282300 | 282300 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 32 | 200000 | 196672.1 | 196672.1 | 170402.1 | 0 | 0 | 0 | 0 | 0
255 | 632 | 33 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 636 | 0 | 400000 | 103207.1 | 103207.1 | 103207.1 | 0 | 0 | 0 | 0 | 6800
255 | 636 | 5 | 200000 | 187913 | 187913 | 39700 | 24286.5 | 11565 | 0 | 0 | 0
255 | 672 | 3 | 1100000 | 487638.96 | 489671.52 | 73317.13 | 460740.6 | 16691.5 | 9377.92 | -303293.23 | 108126.5
255 | 672 | 7 | 400000 | 75552.94 | 75552.94 | 0 | 4706.59 | 15821 | 2400 | 5627.22 | 0
255 | 672 | 9 | 1200000 | 972560.46 | 972560.46 | 92880.67 | 59645.45 | -406064.31 | 5217.12 | 256769.51 | 0
255 | 672 | 10 | 777000 | 0 | 776760.64 | 0 | 0 | 0 | 0 | 0 | 0
255 | 679 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 679 | 2 | 2500000 | 1592298.79 | 1592298.79 | 30580.31 | 583203.35 | 136489.15 | 216456.5 | 272340.94 | 0
255 | 772 | 11 | 6000000 | 5565070.58 | 5571168.26 | 62921.62 | 435021.84 | 3229653.79 | 1013393.35 | 799230.38 | 142502.74
255 | 772 | 16 | 3800000 | 363870.18 | 363870.18 | 0 | 0 | 0 | 360000 | 0 | 0
255 | 772 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 872 | 5 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 872 | 6 | 516000 | 54117.28 | 55827.28 | 0 | 0 | 0 | 0 | 54117.28 | 75797.71
255 | 872 | 7 | 1334000 | 0 | 0 | 16392.08 | 551089 | -729596.46 | -514766.84 | -68133.18 | 0
255 | 910 | 1 | 1307000 | 1252902.15 | 1279070.1 | 84611.53 | 139214.1 | 51414.39 | 181083.66 | 235994.66 | 10051
255 | 910 | 2 | 3900000 | 2929984.25 | 2932670.15 | 245996.29 | 272907.28 | 77390.9 | 870206.37 | -427039.96 | 64524
257 | 636 | 0 | 8000 | 5230.65 | 5230.65 | 0 | 0 | 0 | 1330.65 | 0 | 0
257 | 644 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13926.67
259 | 532 | 6 | 2000000 | 155231.78 | 155231.78 | 0 | 0 | 113447.78 | 0 | 0 | 0
259 | 532 | 7 | 8300 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0
259 | 532 | 8 | 2991800 | 670975.17 | 670975.17 | 0 | 0 | 670975.17 | 0 | 0 | 0
259 | 536 | 11 | 150000 | 30086.16 | 30086.16 | 0 | 0 | 0 | 0 | 0 | 0
259 | 536 | 12 | 600000 | 239960.62 | 239960.62 | 41984.42 | 20992.21 | 1968 | 78542.23 | 57550.11 | 0
259 | 632 | 2 | 2013600 | 1813898.7 | 1813898.7 | 743353.81 | 0 | 135081.45 | 0 | 0 | 0
259 | 632 | 8 | 1007900 | 175387.22 | 175387.22 | 10269.1 | 0 | 84886.91 | 0 | 0 | 0
259 | 632 | 10 | 1300000 | 44942.5 | 44942.5 | 0 | 0 | 42000 | 0 | 2942.5 | 0
260 | 520 | 11 | 3800000 | 3707740.38 | 3707740.38 | 894968.41 | 1454626.54 | 0 | 0 | 0 | 0
260 | 520 | 12 | 4800000 | 203814.19 | 203814.19 | 0 | 0 | 0 | 0 | 0 | 0
260 | 520 | 13 | 1000000 | 307309.23 | 307309.23 | 307309.23 | 0 | 0 | 0 | 0 | 0
260 | 536 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 536 | 4 | 1650000 | 1650000 | 1650000 | 0 | 381360 | 1041926 | 0 | 226714 | 0
260 | 544 | 0 | 24400 | 411.23 | 411.23 | 0 | 0 | 0 | 0 | 0 | 11818.2
260 | 584 | 24 | 6650000 | 1478702.75 | 1478702.75 | 0 | 1256715.7 | 0 | 0 | 221987.05 | 0
260 | 584 | 25 | 250000 | 28800 | 28800 | 0 | 0 | 0 | 0 | 28800 | 0
260 | 584 | 26 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 584 | 27 | 2500000 | 395297.11 | 395297.11 | 154593.21 | 0 | 0 | 0 | 233663.9 | 0
260 | 684 | 14 | 7523900 | 6492896.97 | 6492896.97 | 1726489.83 | 670481.81 | 609499.82 | 1811730.76 | 992226.83 | 0
260 | 784 | 10 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 784 | 12 | 95300 | 95260.46 | 95260.46 | 0 | 0 | 0 | 0 | 0 | 0
260 | 884 | 17 | 6202900 | 3899857.77 | 3899857.77 | 1986675.96 | 354636.04 | 379335.17 | 1179210.6 | 0 | 0
260 | 908 | 2 | 650000 | 622504.03 | 622504.03 | 148257.59 | 43766.06 | 48737.52 | 61303.86 | 40704.16 | 0
260 | 908 | 3 | 650000 | 86921 | 86921 | 13828.1 | 3863.55 | 13619.69 | 16394.05 | 4206.31 | 0
262 | 536 | 0 | 360800 | 41393 | 41393 | 0 | 0 | 25200 | 0 | 10155 | 120500
262 | 536 | 1 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129579
262 | 536 | 4 | 291200 | 291200 | 291200 | 0 | 0 | 41154.56 | 0 | 0 | 0
262 | 544 | 0 | 54600 | 51497.72 | 51497.72 | 2650 | 0 | 0 | 0 | 16540.72 | 0
262 | 584 | 0 | 2800000 | 1237930 | 1237930 | 0 | 420000 | 0 | 817930 | 0 | 0
262 | 810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 836 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 884 | 0 | 1078600 | 795000 | 795000 | 0 | 0 | 0 | 0 | 0 | 0
264 | 532 | 8 | 34500 | 34500 | 34500 | 34500 | 0 | 0 | 0 | 0 | 0
264 | 532 | 9 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 544 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 532 | 2 | 649800 | 70900.36 | 70900.36 | 0 | 0 | 0 | 0 | 70900.36 | 0
266 | 532 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 532 | 5 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 532 | 6 | 400000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0
266 | 536 | 2 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 536 | 3 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 544 | 0 | 18800 | 18715 | 18715 | 0 | 18715 | 0 | 0 | 0 | 0
267 | 536 | 3 | 1800 | 1402.63 | 1402.63 | 0 | 0 | 0 | 0 | 0 | 0
267 | 544 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5692.93
268 | 536 | 0 | 379000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58426
268 | 544 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 73 | 76000 | 75939 | 75939 | 0 | 75939 | 0 | 0 | 0 | 0
270 | 550 | 85 | 180000 | 180000 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0
270 | 550 | 86 | 180000 | 180000 | 180000 | 0 | 0 | 180000 | 0 | 0 | 0
270 | 550 | 87 | 2300 | 2290 | 2290 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 88 | 2300 | 2290 | 2290 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 89 | 2600 | 2595 | 2595 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 90 | 180000 | 180000 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0
270 | 550 | 91 | 496000 | 496000 | 496000 | 0 | 496000 | 0 | 0 | 0 | 0
270 | 550 | 92 | 180000 | 180000 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0
270 | 550 | 93 | 32300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32268.3
270 | 550 | 94 | 22700 | 22624 | 22624 | 0 | 0 | 0 | 0 | 22624 | 0
270 | 550 | 95 | 21100 | 21030 | 21030 | 0 | 0 | 0 | 21030 | 0 | 0
270 | 550 | 96 | 21100 | 21030 | 21030 | 0 | 0 | 0 | 21030 | 0 | 0
270 | 550 | 97 | 177800 | 177708 | 177708 | 0 | 0 | 0 | 177708 | 0 | 0
270 | 550 | 98 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 99 | 360000 | 360000 | 360000 | 0 | 180000 | 180000 | 0 | 0 | 0
270 | 550 | 100 | 85300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81818
270 | 550 | 101 | 276700 | 276613.15 | 276613.15 | 0 | 276613.15 | 0 | 0 | 0 | 0
270 | 550 | 102 | 2842000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841750
270 | 550 | 103 | 3918000 | 3670000 | 3670000 | 0 | 0 | 0 | 0 | 3670000 | 0
270 | 650 | 21 | 0 | 0 | 0 | 0 | -276613.15 | 0 | 0 | 0 | 0
270 | 650 | 24 | 50000 | 0 | 29646 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 237 | 926000 | 925917 | 925917 | 925917 | 0 | 0 | 0 | 0 | 0
271 | 500 | 238 | 1710000 | 1709948 | 1709948 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 239 | 898000 | 897924 | 897924 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 243 | 664900 | 664865 | 664865 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 244 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122426.76
271 | 500 | 245 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 246 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 247 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 248 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 249 | 140000 | 136471.68 | 136471.68 | 0 | 0 | 0 | 0 | 136471.68 | 0
271 | 500 | 250 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 251 | 251600 | 231192 | 231192 | 0 | 0 | 0 | 231192 | 0 | 21424.4
271 | 500 | 252 | 251600 | 231192 | 231192 | 0 | 0 | 0 | 231192 | 0 | 21423.83
271 | 500 | 253 | 206800 | 165010.1 | 165010.1 | 0 | 0 | 0 | 0 | 165010.1 | 7890.83
271 | 500 | 254 | 299000 | 299000 | 299000 | 0 | 299000 | 0 | 0 | 0 | 0
271 | 500 | 255 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 256 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 257 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 258 | 1430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422980
271 | 500 | 259 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 260 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 261 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 262 | 258000 | 258000 | 258000 | 0 | 258000 | 0 | 0 | 0 | 0
271 | 500 | 263 | 258000 | 258000 | 258000 | 0 | 258000 | 0 | 0 | 0 | 0
271 | 500 | 264 | 718500 | 718425 | 718425 | 0 | 0 | 0 | 0 | 718425 | 0
271 | 500 | 265 | 527100 | 527013 | 527013 | 0 | 527013 | 0 | 0 | 0 | 0
271 | 500 | 266 | 140000 | 136471.68 | 136471.68 | 0 | 0 | 0 | 0 | 136471.68 | 0
271 | 500 | 267 | 300000 | 298923.45 | 298923.45 | 0 | 0 | 0 | 0 | 298923.45 | 0
271 | 500 | 268 | 299000 | 299000 | 299000 | 0 | 299000 | 0 | 0 | 0 | 0
271 | 500 | 269 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 270 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 271 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 272 | 277000 | 276925 | 276925 | 0 | 276925 | 0 | 0 | 0 | 0
271 | 500 | 273 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 274 | 277000 | 276925 | 276925 | 0 | 276925 | 0 | 0 | 0 | 0
271 | 500 | 275 | 922000 | 922000 | 922000 | 0 | 0 | 0 | 0 | 922000 | 0
271 | 500 | 276 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127817.8
271 | 500 | 277 | 277000 | 276925 | 276925 | 0 | 276925 | 0 | 0 | 0 | 0
271 | 500 | 278 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 279 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 280 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 281 | 140000 | 136471.68 | 136471.68 | 0 | 0 | 0 | 0 | 136471.68 | 0
271 | 500 | 282 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 283 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 284 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 285 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982903.44
271 | 500 | 286 | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215147.6
271 | 500 | 287 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295029.76
271 | 500 | 288 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 289 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 290 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 291 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 292 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 293 | 205000 | 178595.61 | 178595.61 | 0 | 0 | 0 | 0 | 178595.61 | 0
271 | 500 | 294 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 295 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 296 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 297 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 298 | 115000 | 102715 | 102715 | 0 | 0 | 0 | 0 | 102715 | 0
271 | 500 | 299 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 300 | 302000 | 298923.45 | 298923.45 | 0 | 0 | 0 | 0 | 298923.45 | 0
271 | 500 | 301 | 663500 | 660000 | 660000 | 0 | 660000 | 0 | 0 | 0 | 0
271 | 500 | 302 | 658000 | 598000 | 598000 | 0 | 0 | 0 | 0 | 598000 | 0
271 | 500 | 303 | 2540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2539634
271 | 500 | 304 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 600 | 83 | 207600 | 199914.39 | 199914.39 | 5500.5 | 0 | 552.9 | 8404.08 | 0 | 3626.91
271 | 600 | 84 | 207600 | 199914.39 | 199914.39 | 5500.5 | 0 | 552.9 | 8404.08 | 0 | 3626.91
271 | 600 | 85 | 203600 | 199914.39 | 199914.39 | 5500.5 | 0 | 552.9 | 8404.08 | 0 | 0
271 | 600 | 89 | 210300 | 202878.39 | 202878.39 | 8464.5 | 0 | 552.9 | 8404.08 | 0 | 3626.91
271 | 632 | 1 | 110000 | 37400 | 37400 | 0 | 0 | 0 | 0 | 32200 | 0
272 | 536 | 11 | 50000 | 36428 | 36428 | 0 | 0 | 0 | 0 | 0 | 0
272 | 544 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 536 | 7 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 536 | 8 | 133000 | 132105.4 | 132105.4 | 0 | 0 | 0 | 0 | 0 | 0
273 | 636 | 2 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153000
273 | 636 | 3 | 85000 | 85000 | 85000 | 85000 | 0 | 0 | 0 | 0 | 0
274 | 536 | 5 | 67000 | 23273.47 | 23273.47 | 0 | 0 | 0 | 19473.8 | 3423.67 | 6750
274 | 544 | 0 | 35300 | 35124.89 | 35124.89 | 5072.9 | 0 | 1315.79 | 5440 | 0 | 0
276 | 536 | 14 | 92000 | 63377.6 | 63377.6 | 0 | 0 | 0 | 0 | 0 | 0
277 | 544 | 0 | 1700 | 1634.85 | 1634.85 | 0 | 0 | 0 | 0 | 0 | 0
278 | 536 | 2 | 13000 | 12725.25 | 12725.25 | 0 | 0 | 12725.25 | 0 | 0 | 0
281 | 636 | 3 | 150000 | 89910.73 | 89910.73 | 0 | 0 | 69367.44 | 17210 | 3333.29 | 0
282 | 532 | 6 | 147000 | 31309.34 | 31309.34 | 0 | 0 | 8778.15 | 17564.48 | 4966.71 | 0
282 | 532 | 7 | 576000 | 53450 | 53450 | 0 | 53450 | 0 | 0 | 0 | 0
282 | 532 | 8 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 532 | 9 | 1150000 | 1153774.56 | 1153774.56 | 119554.2 | 0 | 623026.3 | 0 | 411194.06 | 0
282 | 532 | 10 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 532 | 11 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 536 | 1 | 45600 | 44994.4 | 44994.4 | 0 | 0 | 42900 | 2094.4 | 0 | 0
282 | 536 | 36 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 536 | 40 | 760000 | 147391.16 | 147391.16 | -150000 | 92336.58 | 125936.58 | -131938 | 0 | 0
282 | 536 | 41 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 536 | 42 | 1202000 | 1202000 | 1202000 | 0 | 157021.71 | 637992.94 | 42439.46 | 364545.89 | 0
282 | 632 | 2 | 2000000 | 2000000 | 2000000 | 609721.2 | 0 | 267333.8 | 0 | 0 | 0
282 | 632 | 11 | 85000 | 70198.76 | 70198.76 | 2330.72 | 26665.86 | 30211.86 | 0 | 0 | 0
282 | 632 | 12 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 632 | 13 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 632 | 22 | 3330600 | 2571020 | 2571020 | 0 | 0 | 513520 | 420530 | 224920 | 0
282 | 636 | 4 | 150000 | 73792.5 | 73792.5 | 0 | 0 | 28262.5 | 27171 | 18359 | 0
282 | 636 | 7 | 300000 | 225324 | 225324 | 150000 | 0 | 0 | 0 | 0 | 0
282 | 636 | 9 | 2586200 | 823749.71 | 823749.71 | 169417.6 | 192207.81 | 26428.6 | 229046.4 | 174595.3 | 0
282 | 636 | 10 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 636 | 13 | 150000 | 54120.71 | 54120.71 | 0 | 0 | 0 | 0 | 54120.71 | 88587.25
283 | 636 | 0 | 26300 | 26275 | 26275 | 0 | 26275 | 0 | 0 | 0 | 0
283 | 636 | 1 | 4700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 644 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 63985467.83 | 24543723.28
88529191.11