## TECHNICAL AND PLANNING
TECHNICAL AND DEVELOPMENT PLANNING SERVICES DEPARTMENT
2021/2022 - DRAFT SERVICE DELIVERY BUDGET IMPLEMENTATION PLAN
No: | NATIONAL KPA | STRATEGIC OBJECTIVE | PERFORMANCE TARGET | UNIT OF MEASUREMENT | BUDGET | SOURCE OF FUNDING | ANNUAL TARGET | QUARTER ENDING 30 SEPT |  | QUARTER ENDING 31 DEC |  | QUARTER ENDING 31 MARCH |  | QUARTER ENDING 30 JUNE
[8 empty] | TARGET | ACTUAL | TARGET | ACTUAL | TARGET | ACTUAL | TARGET | ACTUAL
1 | DEPARTMENTAL BUDGETING, FINANCIAL MANAGEMENT AND ENSURING MSCOA COMPLIANT
1.1 | FINANCIAL MANAGEMENT AND FINANCIAL VIABILITY | To provide electricity / energy within Mthonjaneni and ensure sound financial management | Ensure 100% spending on MIG annual expenditure programmes with no over-expenditure by 30 June 2022. | Percentage of budgeted amount spent on MIG |  | MIG | 100% MIG spent by 30 June 2022
1.2 |  |  | Ensure 100% spending on INEP grant with no over-expenditure by 30 June 2022. | Percentage of budgeted INEP grant spent. | 20805000 | INEP | 100% of INE P grant to be spent by 30 June 2022
1.3 |  |  | Ensure the submission of the 2021/22 adjustment budget input to CFO by 15 January 2022. | Adjustment budget input submitted to CFO by 15 January 2021. | 0 |  | Submit adjustment budget by 15 Janauary 2022 | _ |  | _ |  | Submit adjustment budget to CFO by 15 January 2022. |  | _
1.4 |  |  | Ensure the submission of the 2022/2023 draft budget proposals to CFO by 28 February 2022 | Draft budget submitted by 28 February 2022 | 0 |  | Submit draft 2022/2023 to CFO by 28 February 2022, | _ |  | _ |  | Submit draftt budget to CFO by 28 February 2022 |  | _
2 | DEPARTMENTAL MANAGEMENT
2.1 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | To ensure proper departmental management and create job opportunities for indigent families | Submit 11 reports to the Technical Services Portfolio Committee on the Performance of Contractors under the control of the Technical Department by 30 June 2022. | Number of reports | 0 | N/A | 11 reports on Contractors submitted to technical portfolio by 30 June 2022. | 3 reports |  | 2 reports |  | 3 reports |  | 3 reports
2.2 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  | Conduct 4 departmental general staff meetings by 30 June 2022 with all Technical services staff and maintain register of meeting minutes. | Number of meetings | 0 | N/A | 4 meetings held by 30 June 2022. | 1 Meeting |  | 1 Meeting |  | 1 Meeting |  | 1 Meeting
2.3 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  | Ensure the submission of all monthly reports to Manco | Monthly Meetings | 0 | N/A | 12 Monthly Reports | 3 reports |  | 3 reports |  | 3 reports |  | 3 reports
2.4 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  | Conduct 11 departmental meetings with all Technical Services management by 30 June 2022 and maintain register of meeting minutes. | Number of meetings | 0 | N/A | 11 DMANCO meetings a held by 30 June 2022. | 3 meeting - DMANCO and 3 meetings |  | 2 meeting - DMANCO meetings |  | 3 meeting - DMANCO and3 meetings |  | 3 meetings - DMANCO meetings
2.5 | GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  | Ensure attendance by Technical & Planning Department of the quarterly meetings of Governance, State Capacity, and Institutional Development (GSCID) cluster meetings. | Number of Quarterly meetings | 0 | N/A | 4 GSCID Cluster Meetings | 1 Meeting |  | 1 Meeting |  | 1 Meeting |  | 1 Meeting
2.6 | COMMUNITY AND SOCIAL DEVELOPMENT |  | Ensure poverty alleviation by creating new 80 EPWP contract jobs by 31 December 2021. | Number of new EPWP jobs created by 31 December 2021 | 1891000 | EPWP Grant | 80 EPWP jobs created by 31 December 2021 | _ |  | Employ 80 EPWP contract workers. |  | _ |  | _
3 | BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENTS
3.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | To ensure that capital budget is spent on capital projects | Ensure the construction and completion of 1.5 km Makhubalo Gravel Road in Ward 9 by 30 June 2022. | Number of kilometers completed | 3472028.14 | MIG | construction and completion of 1.5 km Makhubalo Gravel Road in Ward 9 by 30 June 2022. | Rip and compact 1.5km existing insitu 150 mm thick layer |  | Place and compact 1,5km of 150mm G7/G6 surcing layer |  | Shape road and construct 1,5km earth V-DRAINS AND PIPE CROSSINGS
3.2 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and completion of 5.0 km Ndundulu Gravel Road in Ward 8 by 30 June 2022. | Number of kilometers completed | 7130483.45 | MIG | construction and completion of 5.0 km Ndundulu Gravel Road in Ward 8 by 30 June 2022. | Rip and compact 5.0km existing insitu 150 mm thick layer |  | Place and compact 5,0km of 150mm G7/G6 surcing layer |  | Shape road and construct 5,0km earth V-DRAINS AND PIPE CROSSINGS
3.3 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and completion of 4.0 km Ntilingwane Gravel Road in Ward12 by 30 June 2022. | Number of kilometers completed | 5523505.2 | MIG | construction and completion of 4.0 km Ntlilingwane Gravel Road in Ward 12 by 30 June 2022. | Rip and compact 4.0km existing insitu 150 mm thick layer |  | Place and compact 4,0km of 150mm G7/G6 surcing layer |  | Shape road and construct 4,0km earth V-DRAINS AND PIPE CROSSINGS
3.4 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and completion of Njomelwane Community Hall in Ward 3 by 30 June 2022. | Constrution of Njomelwane Community hall completed | 3846080.7 | MIG | 100% construction and completion of Njomelwane Community hall in Ward 3 by 30 June 2022. | Advertise tender and appoint service provider. |  | Site establishment and construction of sub-structure. (30%) |  | Construction of ablusion blocks and fencing (60%) |  | Grassing,irrigation system and finishes(100%)
3.5 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and completion of Sangoyane sportsfield by 30 June 2022 | Construction of completed Sangoyane sportsfield completed | 3204076.45 | MIG | construction and completion of Sangoyane sportsfield by 30 June 2022
3.6 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and completion of Mahehe Creche in Ward 1 by 30 June 2022. | Constrution of Mahehe Creche completed | 2874537.3 | MIG | 100% construction and completion of Mahehe Creche in Ward 1 by 30 June 2022. | Advertise tender and appoint service provider. |  | Site establishment and BULK EARTHWORKS. (30%) |  | Construction of ablusion blocks and fencing (60%) |  | Grassing,irrigation system and finishes(100%)
4 | OPERATION AND MAINTENANCE (BUILDINGS AND ROADS)
4.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | To maintain council immovable property / assests | Ensure the blading of 3 kilometers of rural access roads in each ward by 30 June 2022. | 3 KM of Access Roads | 200000 | Internal generated funds | completion of maintenance of road infrastructure in 13 wards by 30 June 2022. | blading of 3km in 13 wards
4.2 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the construction and deveolpment of new Cemetries in Ward 2 by 30 June 2022. | Construction and development of new cemetries | 1000000 | Internal generated funds | Completion of newly developed Melmoth cemetry by 30 June 2022 | Site establishment and BULK EARTHWORKS. (30%)
4.3 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  | Ensure the purchasing of protective clothing by 31 December 2021 | Date of purchase | 550000 | Internal generated funds | Purchase protectve clothing | Advertise and appoint service provider |  | Purchase protective clothing. |  | _ |  | _
6 | ELECTRICAL PROJECTS AND ELECTRICAL MAINTENANCE
6.1
6.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | To ensure 20 MVA Thubelethu Bulk Supply | Ensure 20 MVA Substation P-1 Bulk supply upgrade in Ward 2 | upgrading Thubalethu Bulk supply -20mva | 10000000 | INEP | 20 MVA Bulk supply completed by 30 June 2022
6.2 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 35 new connections to households in Nqekwane area ward 1, for the first time by 30 June 2022 | Number of new electricity connections completed | 875000 | INEP | 35 connections completed at Nqekwane in Ward 1, by 30 June 2022.
6.3 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 50 new connections to households in Njomelwane area ward 3, for the first time by 30 June 2022 | Number of new electricity connections completed | 1250000 | INEP | 50 connections completed at Njomelwane in Ward 3, by 30 June 2022.
6.4 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 61 new connections to households in Kataza area ward 4, for the first time by 30 June 2022 | Number of new electricity connections completed | 1525000 | INEP | 61 connections at Kataza in Ward 4, completed by 30 June 2022.
6.5 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 100 new connections to households in Umhlathuze area ward 5, for the first time by 30 June 2022 | Number of new electricity connections completed | 2500000 | INEP | 100 connections completed at Umhlathuze in Ward 5 by 30 June 2022.
6.6 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 25 new connections to households in Dubeni area ward 6, for the first time by 30 June 2022 | Number of new electricity connections completed | 625000 | INEP | 25 connections completed at Dubeni in Ward 6,by 30 June 2022.
6.7 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 85 new connections to households in Inkisa area ward 08, for the first time by 30 June 2022 | Number of new electricity connections completed | 2125000 | INEP | 85 connections at Inkisa in waed 8, completed by 30 June 2022.
6.8 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 42 new connections to households in Ntombokazi area ward 12, for the first time by 30 June 2022 | Number of new electricity connections completed | 105000 | INEP | 42 connections completed at Ntombokazi in ward 12, by 30 June 2022.
6.9 |  | To ensure new connections in our rural area | Ensure the eradication of electrification backlogs in Mthonjaneni by providing 72 new connections to households in Sangoyana area ward 13, for the first time by 30 June 2022 | Number of new electricity connections completed | 1800000 | INEP | 72 connections completed at Sangoyana in Ward 13, by 30 June 2022.
6.1 | SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT | To ensure effective reporting on Meter auditing in Mthonjaneni area | upgrade of thubalethu MV Line by 30 June 2022 | Thubaleth MV Line | 400000 | INEP | Upgrade of thubalethu MV line by 30 June 2022
6.11 |  | To ensure Review of energy Sector plan | Prepare and submit 11 reports to MANCO on meter auditing by 30 June 2022. | Number of electricity meter audit reports submitted to Manco | 0 |  | Submit 11 reports to MANCO by 30 June 2022 | [6 empty] | Final Reiview of terms of reference for Energy sector plan
7 | BACK TO BASICS & INTEGRATED DEVELOPMENT PLAN
7.1 | INSTITUTIONAL DEVELOPMENT AND MUNICIPAL TRANSFORMATION | To ensure reporting on Back to basics | Ensure the submission of 4 quarterly report to MANCO by 30 June 2021. | Number of B2B reports submitted to MANCO | 0 |  | 4 Reports submitted to MANCO by 30 June 2021 | 1 B2B report submitted to MANCO. |  | 1 B2B report submitted to MANCO. |  | 1 B2B report submitted to MANCO. |  | 1 B2B report submitted to MANCO.
7.2 |  |  | Ensure the submittion of the 2022/23 draft IDP Inputs to IDP Unit by 04 March 2022 | IDP Inputs submitted by 04 March 2022 | 0 |  | 2022-03-04 |  |  |  |  | 2022-03-04
7.2 |  | To ensure the new registration of new sites | Ensure the registration of new sites | number of new sites to register | 250000 | Internal generated funds | number of new sites to register by 30 June 2022
7.3 |  | To ensure SDF Development | Ensure the review of the Spatial Development Framework by 30 June 2022 | Date of approval of SDF Plan |  | Internal generated funds | 2022-06-30
Signed by His Worship The Mayor Cllr S.B.K. Biyela:____________________
Note on B19: idp:

## Shadow 02.04.09 (hidden)
Dep-code | Item-code | Vote-code | original | 31/03/2009 | Expenses/income[13] | Expenses/income[10] | Expenses/income[12] | Expenses/income[1] | Expenses/income[2] | Expenses/income[3] | Shadow-costing
201 | 532 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 532 | 2 | 90000 | 72624.46 | 72624.46 | 69624.46 | 3000 | 0 | 0 | 0 | 0
201 | 544 | 2 | 237200 | 148241 | 148241 | 67309 | 0 | 0 | 19440 | 0 | 26845.3
202 | 632 | 2 | 4000000 | 2820887.97 | 2820887.97 | 29042.84 | 0 | 468490 | 89379.77 | 183135.62 | 0
202 | 632 | 3 | 2000000 | 1911060.91 | 1911060.91 | 1053251.14 | 334001.66 | 0 | 226696.45 | 0 | 0
204 | 532 | 10 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 13 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 14 | 16100 | 16100 | 16100 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 15 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 16 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 532 | 17 | 17200 | 17200 | 17200 | 17200 | 0 | 0 | 0 | 0 | 0
204 | 532 | 18 | 40000 | 9100 | 9100 | 0 | 0 | 9100 | 0 | 0 | 0
204 | 536 | 7 | 11300 | 11298 | 11298 | 0 | 0 | 0 | 0 | 0 | 0
204 | 544 | 3 | 23400 | 23391.02 | 23391.02 | 8920 | 0 | 0 | 0 | 0 | 0
204 | 544 | 4 | 19100 | 19040 | 19040 | 0 | 0 | 0 | 695 | 0 | 0
205 | 532 | 5 | 500000 | 418528.52 | 418528.52 | 0 | 418528.52 | 0 | 0 | 0 | 0
205 | 532 | 6 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 536 | 21 | 142800 | 142750.1 | 142750.1 | 0 | 0 | 0 | 0 | 0 | 0
205 | 536 | 22 | 70000 | 59111 | 59111 | 1836 | 0 | 0 | 0 | 11443 | 4990
206 | 532 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 536 | 1 | 7000 | 2028.93 | 2028.93 | 2028.93 | 0 | 0 | 0 | 0 | 0
208 | 544 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 536 | 0 | 30500 | 30447.5 | 30447.5 | 1690 | 0 | 0 | 0 | 0 | 0
209 | 544 | 0 | 10000 | 2200 | 2200 | 0 | 2200 | 0 | 0 | 0 | 6300
210 | 532 | 0 | 6850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 536 | 2 | 23000 | 19842.1 | 19842.1 | 0 | 0 | 17824.56 | 2017.54 | 0 | 0
211 | 536 | 3 | 10000 | 9686.81 | 9686.81 | 0 | 0 | 8684.21 | 1002.6 | 0 | 0
211 | 536 | 4 | 14400 | 12950 | 12950 | 0 | 0 | 0 | 0 | 12950 | 0
211 | 544 | 0 | 12000 | 5447.5 | 5447.5 | 5447.5 | 0 | 0 | 0 | 0 | 0
212 | 532 | 0 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 532 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 536 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 544 | 0 | 11300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8627.5
213 | 536 | 1 | 4400 | 4310 | 4310 | 0 | 0 | 0 | 0 | 0 | 0
213 | 544 | 0 | 35000 | 31430 | 31430 | 16930 | 0 | 0 | 0 | 14500 | 1290
216 | 528 | 0 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 528 | 1 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 11 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 12 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 13 | 70000 | 34500 | 34500 | 34500 | 0 | 0 | 0 | 0 | 0
216 | 532 | 14 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 15 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 16 | 8000 | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0
216 | 532 | 17 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0
216 | 532 | 18 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38780
216 | 532 | 19 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14900
216 | 532 | 20 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94660
216 | 532 | 21 | 1231000 | 137256.04 | 137256.04 | 15200 | 0 | 0 | 0 | 122056.04 | 0
216 | 532 | 22 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 532 | 23 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 536 | 0 | 84000 | 74485.37 | 74485.37 | 0 | 0 | 0 | 0 | 0 | 0
219 | 528 | 2 | 64500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 32 | 400000 | 171671.16 | 171671.16 | 50946.16 | 53351 | 0 | 57974 | 0 | 114512
219 | 532 | 34 | 55000 | 54694.7 | 54694.7 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 35 | 630000 | 439161.53 | 439161.53 | 377764.65 | 0 | 58000 | -7122.81 | 10519.69 | 105327.2
219 | 532 | 38 | 55500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 46 | 470000 | 347676.17 | 347676.17 | 0 | 0 | 0 | 285791.86 | 0 | 66785
219 | 532 | 47 | 24000 | 9305.5 | 9305.5 | 4865.5 | 0 | 0 | 0 | 0 | 0
219 | 532 | 48 | 200000 | 198280 | 198280 | 0 | 0 | 0 | 198280 | 0 | 0
219 | 532 | 49 | 17000 | 6379 | 6379 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 50 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55957.7
219 | 532 | 51 | 2000000 | 184333.79 | 179053.09 | 0 | 0 | 0 | 0 | 184333.79 | 0
219 | 532 | 52 | 35000 | 24490 | 24490 | 0 | 4500 | 0 | 0 | 19990 | 0
219 | 532 | 53 | 150000 | 103100 | 103100 | 0 | 103100 | 0 | 0 | 0 | 0
219 | 532 | 54 | 65000 | 60264.35 | 60264.35 | 0 | 33314.35 | 0 | 26950 | 0 | 0
219 | 532 | 55 | 3000000 | 2086376.41 | 2089877.41 | 281129.05 | 0 | 546491.51 | 0 | 1250219.46 | 30000
219 | 532 | 56 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 57 | 300000 | 116600 | 116600 | 0 | 0 | 0 | 116600 | 0 | 116600
219 | 532 | 58 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 59 | 47500 | 47500 | 47500 | 0 | 47500 | 0 | 0 | 0 | 0
219 | 532 | 60 | 30000 | 17750 | 17750 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 61 | 1000000 | 62830 | 102830 | 0 | 31415 | 0 | 0 | 0 | 100800
219 | 532 | 62 | 7000 | 1680.96 | 1680.96 | 0 | 0 | 0 | 0 | 1680.96 | 0
219 | 532 | 63 | 800000 | 70012.53 | 70012.53 | 0 | 70012.53 | 0 | 0 | 0 | 0
219 | 532 | 64 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 532 | 65 | 72500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000
219 | 532 | 66 | 260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 544 | 0 | 34000 | 30658.6 | 30658.6 | 0 | 30658.6 | 0 | 0 | 0 | 0
219 | 628 | 0 | 1430000 | 1430000 | 1430000 | 0 | 910254.89 | 272005.01 | 0 | 0 | 0
219 | 632 | 17 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 20 | 220000 | 162710.6 | 162710.6 | 14719.6 | 0 | 0 | 0 | 147991 | 35434.5
219 | 632 | 23 | 6610000 | 5070 | 5070 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 24 | 488300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 25 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 26 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 632 | 27 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 532 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 544 | 0 | 1300 | 1208.25 | 1208.25 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 48 | 800000 | 565937.96 | 565937.96 | 0 | 80511.97 | 0 | 248120 | 237305.99 | 224969.85
222 | 572 | 49 | 400000 | 59784.74 | 59784.74 | 0 | 0 | 0 | 0 | 59784.74 | 0
222 | 572 | 50 | 400000 | 0 | 0 | 0 | 0 | -349168.2 | 0 | 0 | 0
222 | 572 | 51 | 829500 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 12320.4
222 | 572 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 56 | 850000 | 315508 | 315508 | 48201.76 | 92370.73 | 0 | 69802.15 | 74056.06 | 0
222 | 572 | 57 | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 58 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 59 | 13035000 | 1767050.54 | 1767050.54 | 0 | 1409507.92 | 357542.62 | 0 | 0 | 0
222 | 572 | 60 | 2000000 | 242887.5 | 242887.5 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 61 | 6110900 | 181065.13 | 181065.13 | 0 | 0 | 0 | 0 | 25829.5 | 0
222 | 572 | 62 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 572 | 63 | 5000000 | 635761.8 | 635761.8 | 0 | 0 | 0 | 0 | 635761.8 | 0
222 | 572 | 64 | 3580700 | 380602.99 | 638314.99 | 0 | 0 | 0 | 55076.72 | 300696 | 0
222 | 572 | 65 | 480000 | 75398.81 | 82733.21 | 11747.48 | 23875.33 | 0 | 26664.3 | 0 | 25242.5
222 | 572 | 66 | 4107000 | 222703.64 | 222703.64 | 0 | 32982.2 | 0 | 80735.11 | 30434.03 | 0
222 | 572 | 67 | 300000 | 7674.33 | 7674.33 | 0 | 0 | 0 | 7345.34 | 328.99 | 127.8
222 | 572 | 68 | 20800000 | 9963293.06 | 9965813.06 | 219428.47 | 518827.71 | 535 | 1433011 | 1998450.43 | 0
222 | 572 | 69 | 3605000 | 3093154.49 | 3093154.49 | 1056484.52 | 2036669.97 | 0 | 0 | 0 | 0
222 | 572 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 591 | 6 | 500000 | 109064.37 | 109064.37 | 0 | 0 | 0 | 109064.37 | 0 | 68503.29
222 | 653 | 0 | 1557700 | 1340000 | 1340000 | 592099.9 | 218218.6 | 17616.62 | 0 | 0 | 0
222 | 672 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 20 | 156600 | 143631.23 | 143631.23 | 59554.97 | 0 | 0 | 34083.46 | 0 | 0
222 | 672 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 22 | 16100 | 16024.07 | 16024.07 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 24 | 600000 | 92922.74 | 92922.74 | 0 | 0 | 0 | 0 | 92922.74 | 1025
222 | 672 | 31 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 40 | 333000 | 311443.08 | 311443.08 | 191567.93 | 0 | 0 | 0 | 0 | 0
222 | 672 | 42 | 11000 | 10339.45 | 10339.45 | 0 | 0 | 0 | 10339.45 | 0 | 0
222 | 672 | 43 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 672 | 45 | 480300 | 49706.5 | 49706.5 | 7026.5 | 0 | 27800 | 14880 | 0 | 0
222 | 672 | 47 | 467000 | 88080 | 88080 | 0 | 0 | 0 | -14880 | 0 | 0
222 | 672 | 48 | 1220400 | 509495.45 | 598604.64 | 509495.45 | 0 | 0 | -10339.45 | 0 | 0
222 | 672 | 49 | 1550000 | 89980.5 | 89980.5 | 0 | 0 | 89980.5 | 0 | 0 | 108779
222 | 672 | 51 | 3755200 | 935388.22 | 935388.22 | 14197.5 | 0 | 0 | 0 | 463850.56 | 0
222 | 672 | 55 | 2800000 | 640943.18 | 640943.18 | 0 | 0 | 0 | 0 | 168834.75 | 0
222 | 672 | 56 | 2225000 | 36905 | 36905 | 0 | 0 | 0 | 0 | 36905 | 0
222 | 691 | 1 | 1965000 | 647053.58 | 647053.58 | 0 | 0 | 0 | 0 | 647053.58 | 0
222 | 772 | 14 | 17401000 | 16946358.41 | 16950683.16 | 0 | 2574036.71 | 57458.39 | 550426.75 | 1268175.6 | 10379
222 | 772 | 16 | 1206400 | 1056431.07 | 1056431.07 | 799798.75 | 0 | 0 | 0 | 0 | 0
222 | 772 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 31 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 32 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 772 | 41 | 801800 | 123162.24 | 123162.24 | 0 | 36302.82 | 74032.45 | 12826.97 | 0 | 0
222 | 772 | 42 | 461800 | 18490.21 | 18490.21 | 0 | 18490.21 | 0 | 0 | 0 | 0
223 | 532 | 2 | 6300 | 6240 | 6240 | 6240 | 0 | 0 | 0 | 0 | 0
223 | 536 | 7 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124760
223 | 544 | 0 | 50000 | 35190 | 35190 | 35190 | 0 | 0 | 0 | 0 | 2450
224 | 528 | 1 | 125000 | 16040 | 16040 | 0 | 0 | 0 | 0 | 0 | 0
224 | 532 | 31 | 1412900 | 1216655.46 | 1216655.46 | 438738.39 | 0 | 177746.67 | 0 | 0 | 0
224 | 532 | 33 | 884000 | 374586.73 | 374586.73 | 34679.64 | 145206 | 4560 | 1980 | 183644.5 | 458000
224 | 532 | 37 | 63500 | 63459.28 | 63459.28 | 21267.68 | 0 | 0 | 0 | 0 | 0
224 | 532 | 38 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0
224 | 532 | 39 | 1240500 | 8205.36 | 8205.36 | 0 | 0 | 8205.36 | 0 | 0 | 1084840
224 | 532 | 40 | 15000000 | 5000000 | 5000000 | 0 | 0 | 0 | 5000000 | 0 | 0
224 | 532 | 42 | 104000 | 101239.04 | 101239.04 | 826.26 | 15000 | 11294 | 0 | 0 | 0
224 | 532 | 43 | 667000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 532 | 44 | 48700 | 48660 | 48660 | 0 | 0 | 0 | 48660 | 0 | 0
224 | 532 | 45 | 120000 | 118610 | 118610 | 0 | 0 | 0 | 59305 | 59305 | 0
224 | 532 | 46 | 171000 | 170465.8 | 170465.8 | 0 | 0 | 0 | 81912.5 | 88553.3 | 328.57
224 | 532 | 47 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 532 | 48 | 46000 | 45912.69 | 45912.69 | 39946.86 | 0 | 0 | 0 | 0 | 0
224 | 536 | 5 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 536 | 6 | 53000 | 4760.6 | 4760.6 | 0 | 0 | 0 | 0 | 0 | 0
224 | 536 | 7 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 572 | 2 | 353400 | 61332.3 | 61332.3 | 0 | 0 | 0 | 0 | 61332.3 | 0
224 | 632 | 7 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 632 | 8 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
224 | 632 | 9 | 370000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 632 | 10 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 632 | 11 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 544 | 0 | 11500 | 7936 | 7936 | 0 | 0 | 0 | 7936 | 0 | 0
227 | 632 | 2 | 9597500 | 7781543.65 | 7781543.65 | 1233217.02 | 0 | 2617996.37 | 415214.45 | 957064.59 | 0
227 | 636 | 0 | 17900 | 17840.34 | 17840.34 | 0 | 0 | 0 | 0 | 0 | 0
228 | 632 | 1 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45350.23
228 | 832 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 89686.08 | -89686.08 | 0
229 | 532 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 532 | 0 | 40000 | 37990 | 37990 | 0 | 0 | 0 | 0 | 37990 | 0
230 | 536 | 3 | 21700 | 21665 | 21665 | 0 | 0 | 0 | 0 | 0 | 0
230 | 544 | 0 | 22500 | 16111 | 16111 | 1551 | 14560 | 0 | 0 | 0 | 0
230 | 644 | 0 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391650.55
233 | 532 | 6 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 536 | 7 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 340800
233 | 536 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 536 | 10 | 436000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341037
233 | 544 | 0 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8376.32
233 | 632 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 632 | 3 | 22100 | 16953 | 16953 | 0 | 14880 | 0 | 0 | 0 | 0
234 | 532 | 21 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 632 | 11 | 877000 | 876213.25 | 876213.25 | 319199 | 14946 | 542068.25 | 0 | 0 | 0
234 | 632 | 14 | 5897800 | 5057266.52 | 5057266.52 | 0 | 817760.32 | 0 | 63570.76 | 3868093.11 | 0
234 | 632 | 15 | 279000 | 72930 | 72930 | 0 | 0 | 35200 | 0 | 0 | 0
234 | 632 | 16 | 399400 | 399400 | 399400 | 0 | 0 | 399400 | 0 | 0 | 0
234 | 632 | 18 | 4239500 | 3843787.49 | 3843787.49 | 76907.72 | 213465.56 | 0 | 247178.73 | 0 | 0
234 | 732 | 12 | 583000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 732 | 13 | 1200000 | 987848.5 | 987848.5 | 400417.5 | 231229.02 | 0 | 0 | 0 | 0
234 | 732 | 14 | 78000 | 77940.38 | 77940.38 | 0 | 0 | 0 | 0 | 0 | 0
234 | 832 | 1 | 12875000 | 7413207.02 | 7413207.02 | 3437527.5 | 988958 | 119982.02 | 0 | 2866739.5 | 0
234 | 832 | 2 | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 532 | 10 | 3500000 | 37950 | 37950 | 0 | 0 | 37950 | 0 | 0 | 0
235 | 832 | 5 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 532 | 5 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24400
238 | 536 | 0 | 10000 | 8771.05 | 8771.05 | 0 | 0 | 0 | 0 | 0 | 0
238 | 544 | 0 | 143600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880
239 | 544 | 0 | 145500 | 146669 | 146669 | 0 | 0 | 0 | 73066 | 73603 | 0
240 | 532 | 1 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 532 | 2 | 76400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 532 | 3 | 22500 | 19248 | 19248 | 0 | 0 | 5530.24 | 0 | 0 | 0
240 | 532 | 4 | 2300 | 2250 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0
240 | 536 | 3 | 30000 | 28847.01 | 28847.01 | 0.01 | 0 | 0 | 0 | 0 | 0
240 | 544 | 2 | 36600 | 34762.6 | 34762.6 | 32905 | 0 | 0 | 0 | 0 | 0
241 | 676 | 1 | 767500 | 592622.6 | 592622.6 | 94500.15 | 22029.86 | 0 | 123661.85 | 51730.29 | 38141.4
241 | 676 | 7 | 300000 | 242114.79 | 242114.79 | 57366.57 | 68441.7 | 1016.28 | 2417.91 | 32992.33 | 4752
241 | 676 | 9 | 146400 | 146309.33 | 146309.33 | 0 | 0 | 0 | 0 | 0 | 0
241 | 676 | 10 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 676 | 11 | 400000 | 302408.9 | 302408.9 | 152235.93 | 7860.62 | 0 | 0 | 0 | 0
241 | 676 | 12 | 200000 | 159910.7 | 159910.7 | 4840 | 0 | 0 | 20704 | 38451.7 | 0
241 | 676 | 13 | 120000 | 119819.72 | 119819.72 | 4400 | 0 | 1760 | 0 | 0 | 0
241 | 676 | 14 | 250000 | 228761.82 | 228761.82 | 0 | 795.2 | 0 | 41260 | 104329.7 | 0
241 | 676 | 15 | 573000 | 62758.44 | 62758.44 | 0 | 0 | 5174.28 | 5174.28 | 46948.14 | 179018
241 | 676 | 16 | 500000 | 19975.8 | 19975.8 | 0 | 13785.8 | 6190 | 0 | 0 | 0
242 | 532 | 23 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 24 | 810000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 25 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 26 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 27 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 532 | 28 | 19900 | 19900 | 19900 | 0 | 0 | 0 | 0 | 0 | 0
242 | 536 | 3 | 40000 | 35908.9 | 35908.9 | 7500 | 0 | 0 | 0 | 0 | 0
242 | 536 | 7 | 30000 | 28210.33 | 28210.33 | 0 | 0 | 28210.33 | 0 | 0 | 0
242 | 536 | 8 | 33000 | 32280.53 | 32280.53 | 0 | 0 | 0 | 0 | 0 | 0
242 | 544 | 0 | 41300 | 20095.47 | 20095.47 | 0 | 0 | 0 | 0 | 0 | 0
242 | 632 | 3 | 1910000 | 1502077.14 | 1502077.14 | 17147.4 | 0 | 0 | 0 | 0 | 0
242 | 632 | 5 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 632 | 6 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 632 | 7 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 536 | 2 | 525500 | 237992.68 | 237992.68 | 41984.4 | 20992.2 | 0 | 78542.31 | 57550.11 | 0
243 | 536 | 3 | 800000 | 202717.62 | 202717.62 | 0 | 0 | 0 | 109350.62 | 66000 | 216912.94
243 | 536 | 7 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 544 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 632 | 0 | 7431100 | 6106603.16 | 6106603.16 | 170089.67 | 1153416.05 | 0 | 3222632.12 | 442171.16 | 387618
243 | 632 | 1 | 2706000 | 97764.77 | 156828.64 | 282400 | 40051.1 | 0 | 917156.8 | 0 | 431066
243 | 632 | 4 | 500000 | 442754.42 | 442754.42 | 99677.9 | 0 | 0 | 0 | 0 | 0
243 | 632 | 6 | 7013500 | 4257093.92 | 4257093.92 | 584300 | 160543.92 | 100800 | -877557 | 0 | 1179576.47
245 | 716 | 2 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 716 | 3 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 716 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 716 | 5 | 567000 | 13911.87 | 13911.87 | 0 | 0 | 0 | 13911.87 | 0 | 159986.53
245 | 716 | 6 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 628 | 0 | 1100000 | 479548.65 | 561144.41 | 0 | 0 | 418522.49 | 0 | 0 | 0
246 | 636 | 1 | 2000000 | 875386 | 875386 | 0 | 0 | 0 | 0 | 875386 | 0
246 | 684 | 1 | 3155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 684 | 3 | 12294700 | 6412996.91 | 6412996.91 | 0 | 2026027.39 | 76235.58 | 508078.44 | 2841721.13 | 0
246 | 884 | 1 | 28718000 | 22322287.58 | 22322287.58 | 6130483.76 | 4394117.46 | 0 | 0 | 8525954.49 | 0
246 | 908 | 1 | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 9 | 50000 | 21690 | 21690 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 22 | 46779000 | 36989207.77 | 36989207.77 | 1520482.76 | 9006604.26 | 0 | 3400629.02 | 17764104.55 | 0
255 | 632 | 23 | 3500000 | 3479129.48 | 3479129.48 | 767812.71 | 156232.37 | 312325.43 | 67839.37 | 172207.64 | 0
255 | 632 | 25 | 3050000 | 3022186.7 | 3022186.7 | 0 | 348429.76 | 0 | 6730.56 | 0 | 0
255 | 632 | 27 | 4600000 | 3718321.14 | 3870420.14 | 188021.77 | 2286.63 | 874399.92 | 7343.78 | 1828464.5 | 716738.5
255 | 632 | 28 | 3100000 | 2963592.03 | 2963592.03 | 0 | 0 | 0 | 0 | 2883211.03 | 0
255 | 632 | 29 | 500000 | 47500 | 47500 | 0 | 0 | 0 | 0 | 47500 | 0
255 | 632 | 30 | 521000 | 268169.81 | 268169.81 | 0 | 0 | 4605.26 | 39125.92 | 224438.63 | 0
255 | 632 | 31 | 437400 | 282300 | 282300 | 0 | 0 | 0 | 0 | 0 | 0
255 | 632 | 32 | 200000 | 196672.1 | 196672.1 | 170402.1 | 0 | 0 | 0 | 0 | 0
255 | 632 | 33 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 636 | 0 | 400000 | 103207.1 | 103207.1 | 103207.1 | 0 | 0 | 0 | 0 | 6800
255 | 636 | 5 | 200000 | 187913 | 187913 | 39700 | 24286.5 | 11565 | 0 | 0 | 0
255 | 672 | 3 | 1100000 | 487638.96 | 489671.52 | 73317.13 | 460740.6 | 16691.5 | 9377.92 | -303293.23 | 108126.5
255 | 672 | 7 | 400000 | 75552.94 | 75552.94 | 0 | 4706.59 | 15821 | 2400 | 5627.22 | 0
255 | 672 | 9 | 1200000 | 972560.46 | 972560.46 | 92880.67 | 59645.45 | -406064.31 | 5217.12 | 256769.51 | 0
255 | 672 | 10 | 777000 | 0 | 776760.64 | 0 | 0 | 0 | 0 | 0 | 0
255 | 679 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 679 | 2 | 2500000 | 1592298.79 | 1592298.79 | 30580.31 | 583203.35 | 136489.15 | 216456.5 | 272340.94 | 0
255 | 772 | 11 | 6000000 | 5565070.58 | 5571168.26 | 62921.62 | 435021.84 | 3229653.79 | 1013393.35 | 799230.38 | 142502.74
255 | 772 | 16 | 3800000 | 363870.18 | 363870.18 | 0 | 0 | 0 | 360000 | 0 | 0
255 | 772 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 872 | 5 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 872 | 6 | 516000 | 54117.28 | 55827.28 | 0 | 0 | 0 | 0 | 54117.28 | 75797.71
255 | 872 | 7 | 1334000 | 0 | 0 | 16392.08 | 551089 | -729596.46 | -514766.84 | -68133.18 | 0
255 | 910 | 1 | 1307000 | 1252902.15 | 1279070.1 | 84611.53 | 139214.1 | 51414.39 | 181083.66 | 235994.66 | 10051
255 | 910 | 2 | 3900000 | 2929984.25 | 2932670.15 | 245996.29 | 272907.28 | 77390.9 | 870206.37 | -427039.96 | 64524
257 | 636 | 0 | 8000 | 5230.65 | 5230.65 | 0 | 0 | 0 | 1330.65 | 0 | 0
257 | 644 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13926.67
259 | 532 | 6 | 2000000 | 155231.78 | 155231.78 | 0 | 0 | 113447.78 | 0 | 0 | 0
259 | 532 | 7 | 8300 | 8250 | 8250 | 0 | 0 | 0 | 0 | 0 | 0
259 | 532 | 8 | 2991800 | 670975.17 | 670975.17 | 0 | 0 | 670975.17 | 0 | 0 | 0
259 | 536 | 11 | 150000 | 30086.16 | 30086.16 | 0 | 0 | 0 | 0 | 0 | 0
259 | 536 | 12 | 600000 | 239960.62 | 239960.62 | 41984.42 | 20992.21 | 1968 | 78542.23 | 57550.11 | 0
259 | 632 | 2 | 2013600 | 1813898.7 | 1813898.7 | 743353.81 | 0 | 135081.45 | 0 | 0 | 0
259 | 632 | 8 | 1007900 | 175387.22 | 175387.22 | 10269.1 | 0 | 84886.91 | 0 | 0 | 0
259 | 632 | 10 | 1300000 | 44942.5 | 44942.5 | 0 | 0 | 42000 | 0 | 2942.5 | 0
260 | 520 | 11 | 3800000 | 3707740.38 | 3707740.38 | 894968.41 | 1454626.54 | 0 | 0 | 0 | 0
260 | 520 | 12 | 4800000 | 203814.19 | 203814.19 | 0 | 0 | 0 | 0 | 0 | 0
260 | 520 | 13 | 1000000 | 307309.23 | 307309.23 | 307309.23 | 0 | 0 | 0 | 0 | 0
260 | 536 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 536 | 4 | 1650000 | 1650000 | 1650000 | 0 | 381360 | 1041926 | 0 | 226714 | 0
260 | 544 | 0 | 24400 | 411.23 | 411.23 | 0 | 0 | 0 | 0 | 0 | 11818.2
260 | 584 | 24 | 6650000 | 1478702.75 | 1478702.75 | 0 | 1256715.7 | 0 | 0 | 221987.05 | 0
260 | 584 | 25 | 250000 | 28800 | 28800 | 0 | 0 | 0 | 0 | 28800 | 0
260 | 584 | 26 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 584 | 27 | 2500000 | 395297.11 | 395297.11 | 154593.21 | 0 | 0 | 0 | 233663.9 | 0
260 | 684 | 14 | 7523900 | 6492896.97 | 6492896.97 | 1726489.83 | 670481.81 | 609499.82 | 1811730.76 | 992226.83 | 0
260 | 784 | 10 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 784 | 12 | 95300 | 95260.46 | 95260.46 | 0 | 0 | 0 | 0 | 0 | 0
260 | 884 | 17 | 6202900 | 3899857.77 | 3899857.77 | 1986675.96 | 354636.04 | 379335.17 | 1179210.6 | 0 | 0
260 | 908 | 2 | 650000 | 622504.03 | 622504.03 | 148257.59 | 43766.06 | 48737.52 | 61303.86 | 40704.16 | 0
260 | 908 | 3 | 650000 | 86921 | 86921 | 13828.1 | 3863.55 | 13619.69 | 16394.05 | 4206.31 | 0
262 | 536 | 0 | 360800 | 41393 | 41393 | 0 | 0 | 25200 | 0 | 10155 | 120500
262 | 536 | 1 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129579
262 | 536 | 4 | 291200 | 291200 | 291200 | 0 | 0 | 41154.56 | 0 | 0 | 0
262 | 544 | 0 | 54600 | 51497.72 | 51497.72 | 2650 | 0 | 0 | 0 | 16540.72 | 0
262 | 584 | 0 | 2800000 | 1237930 | 1237930 | 0 | 420000 | 0 | 817930 | 0 | 0
262 | 810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 836 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 884 | 0 | 1078600 | 795000 | 795000 | 0 | 0 | 0 | 0 | 0 | 0
264 | 532 | 8 | 34500 | 34500 | 34500 | 34500 | 0 | 0 | 0 | 0 | 0
264 | 532 | 9 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 544 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 532 | 2 | 649800 | 70900.36 | 70900.36 | 0 | 0 | 0 | 0 | 70900.36 | 0
266 | 532 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 532 | 5 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 532 | 6 | 400000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0
266 | 536 | 2 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 536 | 3 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 544 | 0 | 18800 | 18715 | 18715 | 0 | 18715 | 0 | 0 | 0 | 0
267 | 536 | 3 | 1800 | 1402.63 | 1402.63 | 0 | 0 | 0 | 0 | 0 | 0
267 | 544 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5692.93
268 | 536 | 0 | 379000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58426
268 | 544 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 73 | 76000 | 75939 | 75939 | 0 | 75939 | 0 | 0 | 0 | 0
270 | 550 | 85 | 180000 | 180000 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0
270 | 550 | 86 | 180000 | 180000 | 180000 | 0 | 0 | 180000 | 0 | 0 | 0
270 | 550 | 87 | 2300 | 2290 | 2290 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 88 | 2300 | 2290 | 2290 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 89 | 2600 | 2595 | 2595 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 90 | 180000 | 180000 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0
270 | 550 | 91 | 496000 | 496000 | 496000 | 0 | 496000 | 0 | 0 | 0 | 0
270 | 550 | 92 | 180000 | 180000 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0
270 | 550 | 93 | 32300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32268.3
270 | 550 | 94 | 22700 | 22624 | 22624 | 0 | 0 | 0 | 0 | 22624 | 0
270 | 550 | 95 | 21100 | 21030 | 21030 | 0 | 0 | 0 | 21030 | 0 | 0
270 | 550 | 96 | 21100 | 21030 | 21030 | 0 | 0 | 0 | 21030 | 0 | 0
270 | 550 | 97 | 177800 | 177708 | 177708 | 0 | 0 | 0 | 177708 | 0 | 0
270 | 550 | 98 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 550 | 99 | 360000 | 360000 | 360000 | 0 | 180000 | 180000 | 0 | 0 | 0
270 | 550 | 100 | 85300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81818
270 | 550 | 101 | 276700 | 276613.15 | 276613.15 | 0 | 276613.15 | 0 | 0 | 0 | 0
270 | 550 | 102 | 2842000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841750
270 | 550 | 103 | 3918000 | 3670000 | 3670000 | 0 | 0 | 0 | 0 | 3670000 | 0
270 | 650 | 21 | 0 | 0 | 0 | 0 | -276613.15 | 0 | 0 | 0 | 0
270 | 650 | 24 | 50000 | 0 | 29646 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 237 | 926000 | 925917 | 925917 | 925917 | 0 | 0 | 0 | 0 | 0
271 | 500 | 238 | 1710000 | 1709948 | 1709948 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 239 | 898000 | 897924 | 897924 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 243 | 664900 | 664865 | 664865 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 244 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122426.76
271 | 500 | 245 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 246 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 247 | 145000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 248 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 249 | 140000 | 136471.68 | 136471.68 | 0 | 0 | 0 | 0 | 136471.68 | 0
271 | 500 | 250 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 251 | 251600 | 231192 | 231192 | 0 | 0 | 0 | 231192 | 0 | 21424.4
271 | 500 | 252 | 251600 | 231192 | 231192 | 0 | 0 | 0 | 231192 | 0 | 21423.83
271 | 500 | 253 | 206800 | 165010.1 | 165010.1 | 0 | 0 | 0 | 0 | 165010.1 | 7890.83
271 | 500 | 254 | 299000 | 299000 | 299000 | 0 | 299000 | 0 | 0 | 0 | 0
271 | 500 | 255 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 256 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 257 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 258 | 1430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422980
271 | 500 | 259 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 260 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 261 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 262 | 258000 | 258000 | 258000 | 0 | 258000 | 0 | 0 | 0 | 0
271 | 500 | 263 | 258000 | 258000 | 258000 | 0 | 258000 | 0 | 0 | 0 | 0
271 | 500 | 264 | 718500 | 718425 | 718425 | 0 | 0 | 0 | 0 | 718425 | 0
271 | 500 | 265 | 527100 | 527013 | 527013 | 0 | 527013 | 0 | 0 | 0 | 0
271 | 500 | 266 | 140000 | 136471.68 | 136471.68 | 0 | 0 | 0 | 0 | 136471.68 | 0
271 | 500 | 267 | 300000 | 298923.45 | 298923.45 | 0 | 0 | 0 | 0 | 298923.45 | 0
271 | 500 | 268 | 299000 | 299000 | 299000 | 0 | 299000 | 0 | 0 | 0 | 0
271 | 500 | 269 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 270 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 271 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 272 | 277000 | 276925 | 276925 | 0 | 276925 | 0 | 0 | 0 | 0
271 | 500 | 273 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 274 | 277000 | 276925 | 276925 | 0 | 276925 | 0 | 0 | 0 | 0
271 | 500 | 275 | 922000 | 922000 | 922000 | 0 | 0 | 0 | 0 | 922000 | 0
271 | 500 | 276 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127817.8
271 | 500 | 277 | 277000 | 276925 | 276925 | 0 | 276925 | 0 | 0 | 0 | 0
271 | 500 | 278 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 279 | 280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 280 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 281 | 140000 | 136471.68 | 136471.68 | 0 | 0 | 0 | 0 | 136471.68 | 0
271 | 500 | 282 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 283 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 284 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 285 | 1080000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982903.44
271 | 500 | 286 | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215147.6
271 | 500 | 287 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295029.76
271 | 500 | 288 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197559.72
271 | 500 | 289 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 290 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 291 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 292 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119738.76
271 | 500 | 293 | 205000 | 178595.61 | 178595.61 | 0 | 0 | 0 | 0 | 178595.61 | 0
271 | 500 | 294 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 295 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 296 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 500 | 297 | 135000 | 115790.76 | 115790.76 | 0 | 0 | 0 | 0 | 115790.76 | 0
271 | 500 | 298 | 115000 | 102715 | 102715 | 0 | 0 | 0 | 0 | 102715 | 0
271 | 500 | 299 | 270000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 245725.86
271 | 500 | 300 | 302000 | 298923.45 | 298923.45 | 0 | 0 | 0 | 0 | 298923.45 | 0
271 | 500 | 301 | 663500 | 660000 | 660000 | 0 | 660000 | 0 | 0 | 0 | 0
271 | 500 | 302 | 658000 | 598000 | 598000 | 0 | 0 | 0 | 0 | 598000 | 0
271 | 500 | 303 | 2540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2539634
271 | 500 | 304 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 600 | 83 | 207600 | 199914.39 | 199914.39 | 5500.5 | 0 | 552.9 | 8404.08 | 0 | 3626.91
271 | 600 | 84 | 207600 | 199914.39 | 199914.39 | 5500.5 | 0 | 552.9 | 8404.08 | 0 | 3626.91
271 | 600 | 85 | 203600 | 199914.39 | 199914.39 | 5500.5 | 0 | 552.9 | 8404.08 | 0 | 0
271 | 600 | 89 | 210300 | 202878.39 | 202878.39 | 8464.5 | 0 | 552.9 | 8404.08 | 0 | 3626.91
271 | 632 | 1 | 110000 | 37400 | 37400 | 0 | 0 | 0 | 0 | 32200 | 0
272 | 536 | 11 | 50000 | 36428 | 36428 | 0 | 0 | 0 | 0 | 0 | 0
272 | 544 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 536 | 7 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 536 | 8 | 133000 | 132105.4 | 132105.4 | 0 | 0 | 0 | 0 | 0 | 0
273 | 636 | 2 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153000
273 | 636 | 3 | 85000 | 85000 | 85000 | 85000 | 0 | 0 | 0 | 0 | 0
274 | 536 | 5 | 67000 | 23273.47 | 23273.47 | 0 | 0 | 0 | 19473.8 | 3423.67 | 6750
274 | 544 | 0 | 35300 | 35124.89 | 35124.89 | 5072.9 | 0 | 1315.79 | 5440 | 0 | 0
276 | 536 | 14 | 92000 | 63377.6 | 63377.6 | 0 | 0 | 0 | 0 | 0 | 0
277 | 544 | 0 | 1700 | 1634.85 | 1634.85 | 0 | 0 | 0 | 0 | 0 | 0
278 | 536 | 2 | 13000 | 12725.25 | 12725.25 | 0 | 0 | 12725.25 | 0 | 0 | 0
281 | 636 | 3 | 150000 | 89910.73 | 89910.73 | 0 | 0 | 69367.44 | 17210 | 3333.29 | 0
282 | 532 | 6 | 147000 | 31309.34 | 31309.34 | 0 | 0 | 8778.15 | 17564.48 | 4966.71 | 0
282 | 532 | 7 | 576000 | 53450 | 53450 | 0 | 53450 | 0 | 0 | 0 | 0
282 | 532 | 8 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 532 | 9 | 1150000 | 1153774.56 | 1153774.56 | 119554.2 | 0 | 623026.3 | 0 | 411194.06 | 0
282 | 532 | 10 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 532 | 11 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 536 | 1 | 45600 | 44994.4 | 44994.4 | 0 | 0 | 42900 | 2094.4 | 0 | 0
282 | 536 | 36 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 536 | 40 | 760000 | 147391.16 | 147391.16 | -150000 | 92336.58 | 125936.58 | -131938 | 0 | 0
282 | 536 | 41 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 536 | 42 | 1202000 | 1202000 | 1202000 | 0 | 157021.71 | 637992.94 | 42439.46 | 364545.89 | 0
282 | 632 | 2 | 2000000 | 2000000 | 2000000 | 609721.2 | 0 | 267333.8 | 0 | 0 | 0
282 | 632 | 11 | 85000 | 70198.76 | 70198.76 | 2330.72 | 26665.86 | 30211.86 | 0 | 0 | 0
282 | 632 | 12 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 632 | 13 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 632 | 22 | 3330600 | 2571020 | 2571020 | 0 | 0 | 513520 | 420530 | 224920 | 0
282 | 636 | 4 | 150000 | 73792.5 | 73792.5 | 0 | 0 | 28262.5 | 27171 | 18359 | 0
282 | 636 | 7 | 300000 | 225324 | 225324 | 150000 | 0 | 0 | 0 | 0 | 0
282 | 636 | 9 | 2586200 | 823749.71 | 823749.71 | 169417.6 | 192207.81 | 26428.6 | 229046.4 | 174595.3 | 0
282 | 636 | 10 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 636 | 13 | 150000 | 54120.71 | 54120.71 | 0 | 0 | 0 | 0 | 54120.71 | 88587.25
283 | 636 | 0 | 26300 | 26275 | 26275 | 0 | 26275 | 0 | 0 | 0 | 0
283 | 636 | 1 | 4700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 644 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 63985467.83 | 24543723.28
88529191.11